## Sheet1
[5 empty] | Week 1 |  |  |  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
 | time axis 2023-01-12 to 2023-04-23
Milestone | Task | Start date | End date | Days | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Meeting | Discussion&brainstorming | 2023-01-12 | 2023-01-20 | 8
Planning | Find methods and models for face recognition | 2023-01-24 | 2023-01-29 | 5
| Find methods and models for dish recognition | 2023-01-24 | 2023-01-31 | 7
| Find an acceleration framework for embedded platforms | 2023-01-26 | 2023-02-04 | 9
Searching | Search information of OpenCV | 2023-02-01 | 2023-02-08 | 7
| Search models and instruction of yolov5-lite | 2023-02-02 | 2023-02-06 | 4
| Learn the usage of QT5 and QT creator | 2023-02-05 | 2023-02-12 | 7
Modelling | Use OpenCV modules to train a face recognition model | 2023-02-09 | 2023-02-20 | 11
| Generate a face recognizer with OpenCV | 2023-02-22 | 2023-03-10 | 16
| Train a dish recognition model with yolov5-lite | 2023-02-09 | 2023-03-10 | 29
| Make a dish recognizer | 2023-03-11 | 2023-03-24 | 13
Interface | QT interface | 2023-03-20 | 2023-04-03 | 14
Code optimisation | Complete driver writing | 2023-04-04 | 2023-04-06 | 2
| Debugging | 2023-04-07 | 2023-04-09 | 2
GitHub | Improve GitHub page (wiki writing, instructions, etc.) | 2023-02-19 | 2023-04-17 | 57